atares  ·  the digital M&A manufactory

STRICTLY CONFIDENTIAL

Project Vision

Proposal for Transaction Advisory Services

Sell-side advisory on the 100% divestment of WTT CampusOne GmbH

Submitted to:

EnBW Energie Baden-Württemberg AG — EKB EnBW Kommunale Beteiligungen GmbH

Attn. Patrick Saporito, Strategic Procurement / Mergers & Acquisitions (cc: Barbara Kuchenmüller)

Submitted by:

Atares GmbH · Prinz-Ludwig-Str. 7 · 80333 München · Jan Pörschmann, Managing Partner

Date: 14 August 2026

Submission deadline: 17 August 2026

Status: Draft for atares internal review — placeholders marked in orange to be confirmed before submission

# Cover letter

Dear Mr. Saporito, dear Ms. Kuchenmüller,

thank you for inviting atares to submit a proposal for Project Vision — the sell-side mandate for EnBW’s 100% divestment of WTT CampusOne GmbH. We would be delighted to act as your Transaction Advisor, and we believe this is a mandate we are exceptionally well suited to lead.

WTT sits at the exact intersection of what atares does best: it is a high-margin, highly recurring, technology-driven B2B software business in the DACH midcap segment, with a defensible position in the energy, utility and municipal markets. As the digital M&A manufactory for technology-driven midcap companies in Germany, we advise almost exclusively on the sell-side of tech transactions, we have completed more than 200 of them, and our EdTech, EnergyTech and public-sector-software credentials map directly onto WTT’s profile.

We have read the RFP carefully and confirm we can deliver the full Scope of Work end-to-end, from preparation through signing and closing. This document responds to each of your points A–J. Where we have made assumptions ahead of data-room access — most importantly on valuation — we have said so clearly. Our preliminary, outside-in view is that WTT’s combination of ~15–20% revenue growth and a ~47% EBITDA margin (a “Rule of 40” score above 60) positions it as a premium, scarcity asset that should attract strong competitive tension from both strategics and financial investors.

We look forward to presenting our proposal in person at your Stuttgart office.

With kind regards,

Jan Pörschmann

Managing Partner · Atares GmbH

# Contents

# Executive summary — why atares for Project Vision

Five reasons atares wins this for EnBW 1. Perfect sector fit. EdTech + EnergyTech + public-sector software — all core atares verticals, with directly relevant sell-side references (H&H → Visma; Adaptricity; mobileX; DC-Software; cadis). 2. A premium asset, priced as one. ~47% EBITDA margin, ~15–20% growth, >80% recurring revenue → Rule of 40 > 60. We will build the process to capture a double-digit EBITDA multiple. 3. Senior-led, stable team. Managing Partner Jan Pörschmann leads throughout, with a dedicated, unchanged core team — exactly as EnBW requires. 4. Unmatched investor access. ~4,000 registered PE funds and ~30,000 corporate-finance contacts across Europe, the Americas and Asia — the reach to run a genuinely international, competitive process. 5. Digital execution edge. The atares deal floor keeps every workstream, document and bidder interaction in one secure, auditable place — speed and control for a carve-out from a listed group.

The remainder of this proposal follows the structure of your RFP (sections A–J), confirms the Scope of Work, and sets out our work plan, indicative timetable and a fully performance-based, capped remuneration model.

# A.  Sector experience & understanding of the business segment

## A.1  Our understanding of WTT and its segment

WTT CampusOne is a leading German EdTech provider of digital learning solutions, headquartered in Ludwigsburg, serving 600+ customers across the DACH region — predominantly Stadtwerke (municipal utilities), energy suppliers and the public sector. Through a proprietary cloud LMS (“eCampus”) it delivers 700+ digital learning modules, with a highly recurring revenue base, strong retention and significant scalability. We understand the segment intimately:

- Regulation is the demand engine. Mandatory, annually-recurring training — occupational safety (ArbSchG/DGUV), data protection (DSGVO), information security (incl. NIS2), compliance and energy-specific obligations — makes revenue non-discretionary and cycle-resilient. The EU AI Act and NIS2 are net-new recurring topics that expand the mandatory catalogue.

- Vertical depth is the moat. Energy- and public-sector-specific content (e.g. Marktkommunikation, grid/metering, §14a EnWG) is content horizontal LMS vendors cannot easily replicate; combined with DSGVO-native data residency, this drives high switching costs in a risk-averse buyer set.

- The market is structurally attractive. German corporate e-learning is growing ~20% p.a. towards ~USD 11bn by 2030, on still-low penetration — a favourable backdrop for the equity story.

## A.2  Relevant atares sell-side transactions

atares has advised on 200+ technology transactions. The references below are directly analogous to Project Vision — recurring-revenue software, public-sector/municipal software, and EnergyTech — spanning both strategic and private-equity acquirers:

| Target (atares sell-side) | Acquirer | Segment | Relevance |
| --- | --- | --- | --- |
| H&H | Visma | Municipal finance software | Public-sector SaaS → strategic |
| Adaptricity | Strategic investors (India) | Grid/network-analysis platform | EnergyTech, cross-border |
| mobileX AG | Solvares Group | Field-service mgmt software | Recurring B2B software |
| DC-Software | FRILO Software | Engineering software | Software buy-and-build |
| cadis® (TMS) | Valsoft Corporation | Vertical SaaS | SaaS → serial acquirer |
| Flexicode | EOS Partners | Software | Software → PE |
| Trivium eSolutions | NetRom & Investcorp | Software engineering | Software → PE-backed |
| Enwendo | Studibo (IceLake Capital) | Tech | Tech → PE |

[atares to confirm which references may be disclosed to EnBW and add anonymised deal metrics (EV, multiple, process length) where permissible — quantified proof points materially strengthen this section.]

# B.  Project manager & core team

EnBW will have a senior-led, commercially oriented and stable team, experienced in the EdTech environment. The mandate is led throughout — preparation, execution and completion — by Managing Partner Jan Pörschmann, in line with your requirement that a senior manager of the firm leads. We commit that the core team will remain unchanged for the duration of the Project.

## B.1  Mandate lead

Jan Pörschmann — Managing Partner. 25+ years as entrepreneur, investor, board member and M&A advisor; 100+ successfully advised transactions over 20 years. Core sector expertise spans IT, media, MarTech, supply-chain tech, EMS, EdTech and business services — a precise match for WTT. EBS alumnus; Munich-based. Jan will personally own the EnBW relationship, the equity story, investor engagement at partner level and the negotiation phase.

## B.2  Proposed core team & time commitment

We propose a lean, senior-heavy team of four, supported by atares’ central research and deal-floor functions. Indicative time commitments reflect a ~9–12 month process:

| Role | Responsibility | Commitment | Phase peak |
| --- | --- | --- | --- |
| Managing Partner — J. Pörschmann | Overall lead, EnBW/steerco, equity story, negotiations | ~30–40% | Throughout |
| Project Director / Partner — [name] | Day-to-day process lead, investor dialogue, DD/Q&A oversight | ~60–70% | Throughout |
| Senior Associate / VP — [name] | Financial model, IM, management presentation, analyses | ~80–100% | Prep + DD |
| Analyst — [name] | Model support, buyer research, data-room, Q&A tracker | ~80–100% | Prep + DD |
| Deal-floor / research (central) | Buyer-universe sourcing (4,000 PE funds), CRM, document control | As needed | Prep + marketing |

[atares to insert the specific named Director, VP and Analyst with one-line bios and photos, confirm % allocations, and add a named EdTech/EnergyTech sector expert if not already on the core team — EnBW explicitly asks for EdTech experience and unchanged staffing.]

Team continuity commitment atares commits that the named core team will remain unchanged throughout the Project, save for reasons outside our control, in which case we will replace like-for-like at equal or greater seniority with EnBW’s prior agreement.

# C.  Current market environment for comparable transactions

The market for high-quality, recurring-revenue B2B software and EdTech assets is active and well-capitalised, on both the strategic and financial-sponsor side. After the 2021 peak and 2022–23 reset, 2024–26 has re-accelerated, driven by AI, buy-and-build consolidation and abundant PE dry powder. Key reference points:

| Reference | EV/Revenue | EV/EBITDA | Type |
| --- | --- | --- | --- |
| Amadeus Fire / Masterplan (09/2025) | ~2.5x | n/a | DE B2B learning, strategic |
| Docebo (listed pure-play LMS) | ~2.1x | ~10.7x | Public comp |
| Instructure / KKR (2024) | ~9x | ~33x | Scale take-private |
| Cornerstone / Clearlake (2021) | ~5x | n/a | PE take-private |
| DACH small-cap software (€5–50m rev) | — | ~7.7–9.7x | Mittelstand band |
| SumTotal / Cornerstone (2022) | ~1.6x | ~5.4x | Mature/low comp |

Read-across for WTT. Listed LMS pure-plays and low-growth assets anchor the bottom of the range; scaled, high-quality take-privates reach 5–9x revenue and 30x+ EBITDA. WTT’s ~47% EBITDA margin and mid-teens growth place it well above the distressed/mature comps and toward the premium end of the DACH software band — the essence of our valuation view in Section E. We will refine the comp set and precedent transactions in the financial model and challenge the internal business case against them, as required by the Scope of Work.

Sources: Aventis Advisors; dealorigination.de (DACH EBITDA multiples 2026); Multiples.vc (Docebo); Amadeus Fire press release; LMS deal debriefs. Full links in the accompanying dossier.

# D.  Equity story & potential investors

## D.1  The equity story

We would develop the equity story with management and EnBW around five pillars, each evidenced by data-room facts:

- Non-discretionary, recurring revenue. >80% recurring, regulation-driven demand with high retention — an annuity-like base that compounds.

- Defensible vertical leadership. The reference platform for energy/utility and municipal learning in DACH, with content and compliance moats horizontal players cannot replicate.

- Proven, profitable growth. ~22% revenue CAGR 2022–25 at an expanding ~47% EBITDA margin — a rare Rule-of-40-plus profile in the midcap.

- Multiple, fundable growth vectors. Cross-/up-sell into the installed base, new compliance topics (EU AI Act, NIS2), adjacent verticals and public administration, DACH-to-international, and price realisation.

- An AI-enabled next chapter. AI in authoring, personalisation and the in-house studio pipeline — converting the sector’s “AI-disruption” narrative into a defensible-AI premium.

## D.2  Buyer universe & atares network

atares maintains direct access to ~4,000 registered PE funds and ~30,000 corporate-finance contacts across Europe, the Americas and Asia — enabling a genuinely international, competitive process. We would prioritise:

| Pool | Illustrative targets (to be refined and prioritised in the buyer long-list) |
| --- | --- |
| Strategics — learning / HR software | Haufe Group, imc AG (Scheer), IU Group, Cornerstone, Docebo, Skillsoft, GoodHabitz, Speexx, 360Learning |
| Strategics — media / publishing / compliance | Klett, Cornelsen, WEKA, Vogel, Forum Verlag, Reguvis, and GRC/compliance-content consolidators |
| Strategics — energy / utility software | Utility-software & services players wanting the Stadtwerke channel (e.g. Schleupen-, items-, powercloud-type buyers) |
| Financial — software/EdTech-focused PE | Hg, Main Capital, Nordic Capital, IK Partners, Verdane, Bregal (Milestone/Unternehmerkapital), Maxburg, DPE, Armira, Keensight, Five Arrows, PSG, TA Associates, Great Hill |
| Financial — buy-and-build platforms | Existing PE-backed learning/compliance platforms seeking a DACH bolt-on |

[atares to convert this into a tiered long-list with specific fund/strategic names, current mandates and warm contacts, and to flag any pre-cleared conflicts — see Section H.]

# E.  Preliminary valuation, value drivers & investor interest

The view below is preliminary and outside-in, based solely on the summary financials in the RFP and public information. It will be replaced by the integrated financial model and confirmed via due diligence. It is intended to frame ranges and support a slider-based discussion in the meeting.

## E.1  The financials point to a premium asset

| €m | 2022 | 2023 | 2024 | 2025 | 2026E | 2028E |
| --- | --- | --- | --- | --- | --- | --- |
| Revenue | 7.0 | 8.5 | 10.8 | 12.8 | 14.7 | 19.5 |
| EBITDA | 2.2 | 3.3 | 4.8 | 6.0 | 7.0 | 10.5 |
| EBITDA margin | 31% | 39% | 44% | 47% | 48% | 54% |

Revenue CAGR 2022–25 ≈ 22%; forecast 2025–28E ≈ 15%; EBITDA margin expanding from 31% to a projected ~54%. A Rule of 40 score above 60 (≈18% growth + 47% margin in 2025) places WTT in the top decile of software assets — the single strongest argument for a premium multiple.

## E.2  Illustrative enterprise-value ranges

Anchored on 2026E EBITDA of €7.0m and 2026E revenue of €14.7m, cross-checked on 2025A:

| Scenario | EV/EBITDA (2026E) | EV/Revenue (2026E) | Illustrative EV |
| --- | --- | --- | --- |
| Conservative | ~9–10x | ~4.0–4.5x | ~€63–70m |
| Base (Rule-of-40 premium) | ~12–13x | ~5.5–6.0x | ~€84–91m |
| Upside (strategic synergy / scarcity) | ~15–16x | ~7.0–7.5x | ~€105–112m |

Indicative EV range ≈ €65–110m, with a base-case centre of gravity around €85–95m. A forward-looking strategic could justify the upper end on 2027–28E earnings and synergies. These figures are illustrative pending the model, normalised (carve-out-adjusted, standalone) EBITDA, net-debt/cash-free and working-capital positions, and confirmed recurring-revenue and churn metrics.

## E.3  Key value drivers (and the diligence that proves them)

- Recurring-revenue quality — contract length, gross vs. net churn, net revenue retention; each point of proven retention supports the multiple.

- Growth durability — new-logo vs. upsell mix, pipeline, price realisation, backlog/ARR bridge.

- Standalone, carve-out-adjusted margin — EBITDA re-based for EnBW shared services, brand and any intercompany terms — decisive for the EBITDA multiple.

- Customer concentration — top-10/20 ARR share; granularity de-risks and lifts value.

- EnBW-independence — the extent to which revenue and channel survive the carve-out (a core diligence and TSA topic).

- Scalability & AI roadmap — gross margin, platform leverage and a credible AI product story.

## E.4  Likely investor interest

We expect strong, two-sided interest. Financial sponsors will be drawn to the recurring, high-margin, regulation-driven cash generation and buy-and-build angle; strategics (learning-software, publishing/compliance, and utility-software players) will value the content moat, the ~600-customer installed base and the Stadtwerke channel. A competitive dual-track of strategics and PE is the best route to maximise value and optionality — and to manage the carve-out and management-continuity considerations.

# F.  Confirmation of Scope of Work, observations & work plan

We confirm we can deliver the full Scope of Work as set out in the RFP — Transaction Structuring & Process Management, the integrated Financial Model, Market Approach, Due Diligence, and Negotiation & Closing support — on an end-to-end basis from preparation through closing, with full transfer of the financial model to EnBW. We accept the 100% share-sale structure and the lead of EnBW’s M&A department supported by internal tax, legal and accounting experts.

## F.1  Work plan (four phases)

| Phase | Key workstreams | Deliverables |
| --- | --- | --- |
| 1. Preparation (Kick-off + ~8–10 wks) | Commercial assessment; equity story with mgmt; integrated financial model & assumptions book; carve-out/TSA scoping; buyer long-list; marketing materials | Model, teaser, IM, mgmt presentation, process letter, buyer list, data-room setup |
| 2. Marketing / Phase 1 | Investor outreach & soundings; NDAs; teaser/IM distribution; Q&A; indicative offers | NDA log, indicative-bid analysis & recommendation |
| 3. Due diligence / Phase 2 | Data room & Q&A management; management presentations (dry runs/coaching); expert sessions; binding offers | DD Q&A, binding-bid comparison, steerco papers |
| 4. Negotiation & closing | SPA negotiation support; final bidder management; signing & closing | Signed SPA, closing checklist, committee/board docs |

## F.2  Observations & additional work we recommend

- Carve-out & TSA readiness is on the critical path. As a divestment from a listed group, clean separation (IT, brand, shared services, intercompany) and a well-defined TSA set materially affect deal certainty and price. We recommend an early carve-out/standalone-cost (“clean EBITDA”) workstream — flagged as additional scope worth resourcing up front.

- Vendor due diligence & fact book. Given the quality of the asset and likely PE interest, a light commercial/financial VDD (or at minimum a vendor fact book and quality-of-earnings support) would accelerate the process and protect value. Not explicitly in scope — we recommend it as an option.

- Management incentivisation & continuity. With the founder-management having largely exited economically, a management-continuity and incentivisation concept (retention, earn-out, and — for PE — new management equity) should be designed early, as buyers price key-person risk into structure. We will support EnBW and management on this.

- Equity-story evidence pack. We will translate the qualitative story into a defensible KPI pack (ARR bridge, cohort retention, pipeline) that survives diligence.

## F.3  Key issues & challenges

- Establishing a credible standalone (post-carve-out) cost base and “clean” EBITDA — the number every buyer will anchor on.

- Demonstrating EnBW-independence of revenue and the Stadtwerke channel post-separation.

- Managing a compressed, high-quality process to sustain competitive tension across an international buyer pool.

- Management availability and readiness for presentations while running the business.

# G.  Process set-up & indicative timetable

We propose a controlled, competitive dual-track (strategics + financial sponsors) process, kicking off end September/October per the RFP, targeting signing around mid-2027. Indicative timeline (to be confirmed at kick-off):

| Period | Milestone | In-person / workshops |
| --- | --- | --- |
| Late Sep / Oct 2026 | Kick-off; preparation phase begins | Kick-off & equity-story workshop (Stuttgart) |
| Oct–Dec 2026 | Model, IM, buyer list, data-room build; carve-out scoping | Management workshops; steerco #1 |
| Jan–Feb 2027 | Phase 1 launch: outreach, NDAs, IM, indicative offers | Steerco #2 (bid review) |
| Mar–May 2027 | Phase 2: due diligence, mgmt presentations, binding offers | In-person management presentations & site visits; dry runs |
| Jun–Jul 2027 | SPA negotiation; signing | Negotiation sessions; steerco #3 |
| Thereafter | Closing (conditions precedent) | Closing |

In-person cadence. We favour face-to-face working: a kick-off/equity-story workshop and management workshops in the preparation phase, in-person steering-committee meetings at each decision gate, and in-person management presentations and negotiation sessions in Phase 2 — with our lead team present throughout. We are happy to base key sessions at EnBW’s Stuttgart office.

[Timetable is indicative; overall duration (~9–12 months to signing) and gate dates to be confirmed with EnBW at kick-off.]

# H.  Confirmation of no conflict of interest

atares confirms that, to the best of its knowledge, it has no conflict of interest that would impair its ability to act as Transaction Advisor to EnBW on Project Vision. We do not currently act for WTT CampusOne, for any party we would expect to be a bidder in a capacity that conflicts with this mandate, nor do we hold any interest in the target.

We operate strict confidentiality and information-barrier procedures, will treat all RFP and Project information as strictly confidential, and will run a documented conflict check against the final buyer long-list before any outreach, disclosing and clearing any potential conflict with EnBW in advance.

Action before submission [atares compliance to run a formal conflict check against WTT, EnBW/EKB and the draft buyer universe, and confirm this statement — or disclose and ring-fence any specific relationship — prior to sending the proposal.]

# I.  Remuneration model

Our proposal is performance-based and capped, fully aligned with EnBW’s objective of maximising value, with any retainer fully creditable against the success fee — exactly as requested.

## I.1  Structure

| Component | Proposal (indicative — to be finalised) |
| --- | --- |
| Retainer | Modest monthly retainer for a defined period, FULLY CREDITABLE against the success fee (i.e. deducted from it at closing). Covers preparation-phase resourcing only. |
| Base success fee | A percentage of transaction enterprise value, payable only on a successful closing. |
| Incentive ratchet | An increased marginal fee rate on value achieved ABOVE an agreed threshold EV — so atares is rewarded specifically for out-performance. |
| Cap | Total fees capped at an agreed maximum amount, giving EnBW certainty. |
| Expenses | Reasonable, pre-agreed out-of-pocket expenses at cost; EnBW bears no RFP-response costs. |

## I.2  Illustrative scale

[atares to insert firm-approved figures. Typical shape for a mandate of this size, purely illustrative: retainer €[15–25]k/month for [4–6] months (creditable); base success fee ≈ [1.5–2.5]% of EV; ratchet of ≈ [3–5]% on EV above €[90–95]m; overall cap €[•]. Confirm all numbers with atares management before submission.]

Alignment Because the retainer is fully creditable and the upside is concentrated in the ratchet above a threshold, atares only earns materially when EnBW achieves an above-expectation outcome — a clean alignment of interests, with a cap for budget certainty.

# J.  Other relevant information

- The atares deal floor. Our cloud platform holds all processes, leads, documents and deal content securely and auditably in one place — giving EnBW real-time transparency and tight control, valuable for a listed-group carve-out.

- International reach, local delivery. Munich-based senior team, ~30,000 corporate-finance contacts and ~4,000 PE relationships across Europe, the Americas and Asia — the network to reach international buyers while running the process in German and English.

- Bilingual materials. All external documents and the financial model will be prepared to be suitable for both German and international investors.

- References. We are happy to provide client references from comparable sell-side software/EdTech mandates on request.

- [atares to add: any energy-sector / Stadtwerke relationships that aid buyer access; ESG/《Made in Germany》 angle for the equity story; and named case studies with permission.]

# Important notice & caveats

This proposal is a draft prepared for atares’ internal review. Items marked in orange require confirmation by atares before submission (team names, fee figures, conflict check, disclosable references). Financials are taken from EnBW’s RFP; all valuation figures are preliminary, outside-in and illustrative, to be replaced by the integrated financial model and confirmed in due diligence. Nothing herein constitutes a binding offer. All EnBW information is treated as strictly confidential.

### Selected sources

- atares — firm & team

- Jan Pörschmann — atares

- atares — transactions

- Aventis Advisors — SaaS multiples

- dealorigination.de — DACH EBITDA multiples 2026

- Amadeus Fire / Masterplan